Lab 3 Part A — Apply the six selection questions

For each question, answer for YOUR client and say what it pushes you toward. Every answer must point at a fact in the client brief or your Week 2 notes — not a general opinion about the model.

| Selection question | Your answer for this client (Kina Ridge Primary School) | Pushes toward… |
| --- | --- | --- |
| How well understood are the requirements? | There is general understanding of core school requirements (student records, attendance, tracking and reporting fees) but some school processes may be adjusted upon staff exposure to the system. | Incremental / Agile |
| Can the client engage continuously? | The head teacher is unable to be present on a daily basis due to the demands of school running. Twice a week reviews are more feasible. | Blended approach |
| What does the contract or funding demand? | The school will need to have concrete milestones; progress reports and approval is likely to be required before full deployment. | Plan-driven elements |
| How big is the team, and where is it? | A small student development team, located at an off-site from the school. | Incremental delivery |
| What is the cost of failure? | Loss of student records, attendance data or fee payments would cause operational problems for the school. | Strong testing and verification |
| How fast must value appear for this client? | The school can benefit immediately from attendance and student-record management. | Incremental development |

Lab 3 Part B — Choose and justify

A blended approach combining incremental software delivery with formal project review checkpoints

The blended lifecycle that combines incremental development with formal review points is most suitable for Kina Ridge Primary School. The school's main requirements, such as student records, attendance tracking, and fee management, are generally understood, but some details may change once teachers begin using the system. Incremental delivery allows working software to be provided early so feedback can be gathered before the entire system is completed.

This approach is influenced by client availability. The head teacher and staff have regular responsibilities and cannot provide daily involvement. Therefore, a pure Scrum approach is unrealistic, and review meetings will be conducted fortnightly. The project team is small and likely distributed, making short development cycles practical.

One argument against incremental development is the need for accurate school data. Errors in attendance records, student information, or payment details could create significant operational problems. These risks will be managed through thorough testing, reliable backups, validation with school staff, and formal approval at each milestone. This app

Lab 3 Part C — Plan three increments

| Increment | What It Delivers | Why This Order? | Rough Duration & Why |
| --- | --- | --- | --- |
| 1 | Student Registration and Attendance Management System. Enables teachers to register students and record daily attendance. | Delivered first because it provides immediate value to the school and can be used as soon as it is implemented. Attendance management is a core daily activity. | 3 Weeks. Requires development of essential system features and testing to ensure reliable daily use. |
| 2 | School Fee and Payment Tracking Module. Allows the school to record, monitor, and manage student fee payments. | Implemented after Increment 1 because payment records must be linked to student information already stored in the system. | 3 Weeks. Needs integration with the student database and validation of payment records. |
| 3 | Reporting, Analytics, and Administrative Dashboard. Provides reports and insights for school management and decision-making. | Delivered last because it depends on data generated from student records, attendance, and fee management functions. | 2 Weeks. Uses existing system data to generate reports and administrative information. |

C4. Delivery-condition check — for each increment, note one PNG delivery condition that affects when or how you can deliver it (client travel, power, connectivity, harvest or school-term timing, committee approval cycles).

| Increment | Delivery condition |
| --- | --- |
| 1 | Delivery should be scheduled during the school term when teachers are available for training and can start using the student registration and attendance system immediately. |
| 2 | Implementation depends on access to existing payment records and approval from the school administration to ensure accurate fee management. |
| 3 | Final delivery requires a school management review and reliable power or internet connectivity for testing, demonstration, and deployment. |

Lab 3 Part D — Reflect

D1. If the client suddenly demanded ALL three increments by the same original deadline, which corner of the dependency triangle would you push back on — and what exactly would you say to them? Write the actual sentence you would say.

I would push back on the project scope and say, to meet the original deadline while maintaining quality, we will deliver student registration, attendance, and fee management first, while moving less critical reporting features to a later release.

D2. Which of your three increments is most likely to change after the client sees Increment 1? What does that tell you about how firmly to specify it now?

Increment 3 is most likely to change after users begin using Increment 1, so its reporting requirements should remain flexible until feedback is collected from teachers and administrators.