Estimation Workshop

Part A and B – Break down Increments and Estimate each task.

Increment 1: Student Enrollment and Attendance System

| # | Task | O | M | P | E | SD | Assumption behind it |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Requirements gathering | 4 | 8 | 16 | 8.67 | 2 | Non Coding |
| 2 | Database design and setup | 6 | 10 | 18 | 10.67 | 2 |  |
| 3 | Student registration interface | 10 | 16 | 28 | 17 | 3 |  |
| 4 | Student records management | 8 | 14 | 26 | 15 | 3 |  |
| 5 | Attendance tracking module | 12 | 18 | 32 | 19.33 | 3.33 |  |
| 6 | User authentication and security | 6 | 10 | 18 | 10.67 | 2 |  |
| 7 | System testing and debugging | 8 | 12 | 22 | 13 | 2.33 | Non Coding |
| 8 | User training and deployment | 4 | 8 | 16 | 8.67 | 2 | Non Coding |
| Total |  |  |  |  | 103.01h | 19.66 |  |

- (M) = 8 + 10 + 16 + 14 + 18 + 10 + 12 + 8 = 96.0 h

- PERT expected total = 103.01 h

- Gap between M and PERT = 103.01 − 96.0 = 7.01 h

- Percentage gap = (7.01 ÷ 96.0) × 100 = 7.3%

- Non-coding work

  - Requirements gathering = 8.67 h

  - System testing and debugging = 13.00 h

  - User training and deployment = 8.67 h

Total non-coding work = 30.34 h

- Percentage non-coding = (30.34 ÷ 103.01) × 100 = 29.4%

- At 15 productive hours per week

=103.01 ÷ 15 = 69

= 6.9 weeks

Increment 2: School Fee Collection and Payment Monitoring

| # | Task | O | M | P | E | SD | Assumption behind it |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Fee structure configuration | 4 | 7 | 14 | 7.67 | 1.67 |  |
| 2 | Payment database integration | 6 | 10 | 18 | 10.67 | 2 |  |
| 3 | Payment entry module | 10 | 14 | 24 | 15 | 2.33 |  |
| 4 | Receipt generation feature | 8 | 12 | 20 | 12.67 | 2 |  |
| 5 | Balance monitoring function | 8 | 12 | 22 | 13 | 2.33 |  |
| 6 | Payment verification processes | 6 | 10 | 18 | 10.67 | 2 |  |
| 7 | System validation testing | 6 | 9 | 16 | 9.67 | 1.67 | Non coding |
| 8 | Staff training and implementation | 4 | 7 | 14 | 7.67 | 1.67 | Non coding |
| Total |  |  |  |  | 87.02h | 15.67 |  |

- (M) alone = 7 + 10 + 14 + 12 + 12 + 10 + 9 + 7 = 81.0 h

- PERT expected total = 87.02 h

- Gap between M and PERT = 87.02 − 81.0 = 6.02 h

- Percentage gap = (6.02 ÷ 81.0) × 100 = 7.4%

- Non-coding work

  - System validation testing = 9.67 h

  - Staff training and implementation = 7.67 h

Total non-coding work = 17.34 h

- Percentage non-coding = (17.34 ÷ 87.02) × 100 = 19.9%

- At 17.5 productive hours per week

= 87.02 ÷ 17.5 = 5

= 5 weeks

Increment 3: Reporting, Analytics and Administrative Dashboard

| # | Task | O | M | P | E | SD | Assumption behind it |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Dashboard requirements analysis | 5 | 8 | 16 | 8.83 | 1.83 | Non coding |
| 2 | Dashboard interface development | 8 | 12 | 22 | 13 | 2.33 |  |
| 3 | Attendance reporting module | 8 | 12 | 24 | 13.33 | 2.67 |  |
| 4 | Fee payment reporting module | 8 | 12 | 24 | 13.33 | 2.67 |  |
| 5 | Data analytics functionality | 10 | 15 | 28 | 16.33 | 3 |  |
| 6 | Administrative dashboard integration | 8 | 12 | 24 | 13.33 | 2.67 |  |
| 7 | Report testing and validation | 6 | 10 | 18 | 10.67 | 2 | Non coding |
| 8 | User acceptance and deployment | 5 | 8 | 16 | 8.83 | 1.83 | Non coding |
| Total |  |  |  |  | 97.65 | 19 |  |
| 10 |  |  |  |  |  |  |  |

- (M) alone = 8 + 12 + 12 + 12 + 15 + 12 + 10 + 8 = 89.0 h

- PERT expected total = 97.65 h

- Gap between M and PERT = 97.65 − 89.0 = 8.65 h

- Percentage gap = (8.65 ÷ 89.0) × 100 = 9.7%

- Non-coding work:

  - Dashboard requirements analysis = 8.83 h

  - Report testing and validation = 10.67 h

  - User acceptance and deployment = 8.83 h

  - Total non-coding work = 28.33 h

- Percentage non-coding = (28.33 ÷ 97.65) × 100 = 29.0%

- At 16.3 productive hours per week:

= 97.65 ÷ 16.3 = 6

= 6 weeks

Combined Standard Deviation

Using increment SD totals

- Increment 1 SD = 19.66

- Increment 2 SD = 15.67

- Increment 3 SD = 19.10

=19.662+15.672+19.102

=386.52+245.55+364.81

=996.88
=31.57 hours

Combined Standard Deviation

SD = 31.57 hours

Honest Range Calculation

Total Estimated Hours (E):

103.01+87.02+97.65=287.68 h

Lower Estimate = E-SD=287.68-31.57=256.11 h

Upper Estimate = E+SD=287.68+31.57=319.25 h

At 16 productive hours/week:

256.11÷16=16.0 weeks
319.25÷16=20.0 weeks

Part C — Convert to a calendar (20 min)

| Question | Your answer |
| --- | --- |
| How many PRODUCTIVE hours per week can you truly give this project? (Count your other units.) | Approximately 16 hours per week |
| Total E ÷ productive hours per week = how many weeks? | Total E = 103.01 + 87.02 + 97.65 = 287.68 hours. 287.68 ÷ 16 = 17.98 weeks |
| Same calculation using E − SD and E + SD → your honest range | Total SD = 19.66 + 15.67 + 19.10 = 54.43 hours. Lower: (287.68 − 54.43) ÷ 16 = 14.6 weeks. Upper: (287.68 + 54.43) ÷ 16 = 21.4 weeks |
| Which PNG factors will stretch this? (client availability, travel, power, term dates, holidays) | Availability of clients, power failures, internet access, exam dates at the university, travel needs, public holidays, test deployment challenges delays. |
| Adjusted finish, stated as a range | 16–20 (Range) weeks most likely duration of 18 weeks. |

Part D — Build the schedule

| Increment | What it delivers | Milestone the client can see | Weeks |
| --- | --- | --- | --- |
| 1 | Registration of students, Student record management, Attendance, User authentication and security. | Students are successfully registered in to the system by school staff, and attendance is updated and recorded by staff. | Week1-7 |
| 2 | Fee configuration, processing, receipt generation, monitoring and payment verification. | The bursar notes the payment and checks the amount is correct. They update the account balance right after that. Then they print a receipt for the record. | Weeks 8-12 |
| 3 | Attendance reports, payment reports, analytics functions and administration dashboard. | The school administration makes reports. It also checks who shows up, and it looks at payment totals. All of this is shown in the dashboard, along with some basic charts and statistics. | Week 13-18 |

AI Deceleration:  Microsoft Copilot was used to assist in decomposing the software increments into smaller tasks (6–12 tasks per increment) for estimation and planning purposes.