Western Pacific University

Department of Emerging

&

Computing Technologies

CMN 224   Software Engineering

Lab 1: Software Success & Failure Analysis

Case: Healthcare.gov launch (USA, 2013) — national website collapsed at launch under real load.

Group Members

- Justin Albert

- Yop Hulda

- What was the system meant to do, and for whom? (One paragraph.)

Healthcare.gov was established by the Affordable Care Act (ACA) to serve an online health insurance marketplace of Americans to use to compare health insurance plans, determine financial eligibility and enrol in health insurance coverage. The system was primarily created to serve uninsured citizens who are looking for low-cost health care. Key stakeholders were the centres of Medicare and Medicaid Services (CMS), the Department of Health and Human Services (HHS), White House, insurance companies, the IRS the Social Security, contractors such as CGI and QSSI, and the American public.

2.What happened? Timeline of key events with your sources.

| Date | Event |
| --- | --- |
| March 2010 | President Obama signed the Affordable Care Act (ACA) into law. |
| September 2011 | CMS awarded contracts to multiple vendors, including CGI. |
| December 2011 | Development of Healthcare.gov officially began. |
| April 2013 | McKinsey released a report warning about project risks such as poor governance, inadequate testing, and leadership issues. |
| September 2013 | CMS identified 45 critical defects and 324 serious defects but decided to proceed with the launch. |
| 1 October 2013 | Healthcare.gov launched nationwide. More than 4 million users visited the site, but only 6 successfully enrolled on the first day. |
| October 2013 | The website experienced crashes, slow performance, registration failures, and enrolment errors. |
| Late October 2013 | A recovery effort began under Jeffrey Zients. A Tiger Team was formed to fix major problems. |
| December 2013 | Around 400 defects were fixed, and enrolment increased from 26,000 in October to 975,000 users. |
| 2014 | CGI was replaced by Accenture. Total project costs eventually exceeded $1.7 billion. |

- Which of the four process activities broke down (or worked well): specification, development, validation, evolution? Justify.

Specification (Failed)

Specification is about defining and controlling the requirements of a system. Due to changing requirements during the project, Healthcare.gov had numerous specification issues. Late in development, decisions were made and new requirements were introduced by various government agencies. For example, implementing an authentication system where the user must register before being able to view insurance plans added to the system complexity just weeks before the launch. As scope was continually expanded, there was a difficulty in completing and testing the system in a proper manner.

Development (Failed)

Development suffered because responsibility was distributed across many contractors with no clear leadership. Over 30 vendors were working on multiple parts of the system, and there was no obvious lead system integrator that was coordinating all elements. Consequently, the website, data services hub, identity-management system and external databases were not effectively linked. Software defects and performance problems were also caused by poor coding and lack of oversight.

Validation (Major Failure)

Validation is the test of the system to verify that the system is meeting the requirement. This was the worst result of this project. There was inadequate and late testing. Though millions were expected to use the platform, the identity-management system was tested at a low number of simultaneously using users around 2,000. Prior to launch there were a significant number of known critical defects that were still not addressed. Consequently, the system failed under the actual usage.

Evolution (Successful)

The process of evolution is to enhance and maintain software following deployment. While the opening of Healthcare.gov was a failure, the recovery was a success. The Tiger Team adopted the agile practices, focused on critical defects, enhanced system performance, and added capacity. The website was then made operational, and the numbers of enrolments rose within weeks

- Which attributes of good software were violated or achieved: maintainability, dependability & security, efficiency, acceptability?

Maintainability (Partially Achieved)

At first, Healthcare.gov struggled to sustain as there was an absence of effective vendor management, and a lot of vendors worked independently. The successful repairs of hundreds of defects within a few weeks, however, showed that it was possible to change and improve the system. As a result, only partial success was achieved in maintaining.

Dependability and Security (violated)

Dependability requires software to operate reliably and securely. Healthcare.gov failed in this area because users experienced crashes, failed registrations, duplicate enrolments, and service outages. Security audits also identified weaknesses such as insecure transmission of data, weak password reset processes, and privacy concerns. These issues reduced trust in the system.

Efficiency (Violated)

Healthcare.gov suffered from severe performance problems. Pages loaded slowly, some registration processes took over a minute, and servers could not handle expected traffic volumes. The infrastructure was poorly configured and tested, resulting in poor efficiency.

Acceptability (Initially Violated, Later Improved)

At launch, the system was frustrating and difficult to use, causing public criticism and negative media attention. However, the Tiger Team quickly fixed hundreds of defects, improved performance, and made the website stable enough to support large numbers of users.

- Name TWO software engineering practices that would most likely have changed the outcome and say why.

- Agile Development (Scrum)

One practice that could have significantly improved Healthcare.gov was the adoption of a true Agile development approach. Agile methods emphasize incremental development, continuous feedback, regular testing, and close collaboration among teams.

Healthcare.gov was managed more like a traditional waterfall project where integration occurred near the end. If Agile practices had been used consistently, defects and integration problems could have been discovered much earlier. Frequent reviews and sprint demonstrations would have improved visibility, accountability, and communication among contractors and government agencies.

- Phased Rollout and Comprehensive Testing

Another practice that would likely have prevented failure was a phased rollout combined with extensive end-to-end testing. Instead of launching the website to the entire country at once, CMS could have released it first to a smaller group of users or specific regions. This approach would have allowed developers to identify performance bottlenecks, capacity issues, and security weaknesses before national deployment. Comprehensive load testing and integration testing would also have revealed many of the problems that caused the launch failure. A phased rollout would have reduced risk and improved system reliability.

- PNG lens: what would an engineer in PNG learn from this case for local delivery conditions?

A PNG engineer would learn the importance of strong leadership, clear requirements, thorough testing, and gradual deployment. Instead of launching a large system all at once, projects should start with a simple version (MVP), test it with a small user group, and expand gradually. The case shows that even well-funded projects can fail if planning, coordination, and testing are weak.

References

https://www.henricodolfing.ch/en/case-study-17-the-disastrous-launch-of-healthcare-gov/

https://hackernoon.com/small-is-beautiful-the-launch-failure-of-healthcare-gov-5e60f20eb967